## Progress_20150315
No. | Task (class name) | Category | undertaker | due date | Specification | progress(%) | 16 Mar. - 20 Mar. | 23 Mar. - 27 Mar. | 30 Mar - 4 Apr.
1 | Storekeeper | domain | Charan | 2015-03-20 | Mgr,Dao,TestCase
2 | Customer(Abstract) | domain | Achyut | 2015-03-20
3 | Member | domain | Achyut | 2015-03-20 | Mgr,Dao,TestCase
4 | Public | domain | Achyut | 2015-03-20
5 | Transaction | domain | Liu Xinzhuo | 2015-03-20 | Mgr,Dao,TestCase | 70
6 | TransactionItem | domain | Liu Xinzhuo | 2015-03-20 | TestCase | 70
7 | Product | domain | Xie Jiabao | 2015-03-20 | Mgr,Dao,TestCase
8 | Category | domain | Avishek | 2015-03-20 | Mgr,Dao,TestCase
9 | Vendor | domain | Avishek | 2015-03-20 | Mgr,Dao,TestCase
10 | PurchaseOrder | domain(expanded) | Xie Jiabao | 2015-03-20 | TestCase
11 | Discount(Abstract) | domain | Tanuj | 2015-03-20 | Mgr,Dao
12 | MemberDiscount | domain | Tanuj | 2015-03-20 | TestCase
13 | OccasionalDiscount | domain | Tanuj | 2015-03-20 | TestCase
14 | Store | domain | Xu Minsheng | 2015-03-20 | TestCase | 20
15 | StoreApplication | Controller | Xu Minsheng |  |  | 20
16 | LoginScreen | UI | Charan | 2015-03-27
17 | MainMenu | UI | Charan | 2015-03-27
18 | CheckOutScreen | UI | Liu Xinzhuo | 2015-03-27 | Check Out process. print receipt. | 50
19 | CheckInventoryScreen | UI | Xie Jiabao | 2015-03-27 | generate purchase order and print to console
20 | MemberListScreen | UI(expanded) | Achyut | 2015-03-27 | List all. Provide DELETE function?
21 | MemberDialog | UI | Achyut | 2015-03-27 | Create. Update?
22 | ProductListScreen | UI(expanded) | Xie Jiabao | 2015-03-27 | List all. Provide DELETE function?
23 | ProductDialog | UI | Xie Jiabao | 2015-03-27 | Create. Update?
24 | CategoryListScreen | UI(expanded) | Avishek | 2015-03-27 | List all. Provide DELETE function?
25 | CategoryDialog | UI | Avishek | 2015-03-27 | Create. Update?
26 | NewVendorDialog | UI | Avishek | 2015-03-27 | Create. Update?
27 | ReportScreen | UI | Charan | 2015-03-27 | 4 kinds of report ? Or just for transaction?
28 | Placeholder | Other | Tanuj | 2015-03-27 | barcode reader/printer, receipt printer
29 | Util | Other | Xu Minsheng | 2015-03-27 |  | 20
30 | OtherExceptions | Other | Xu Minsheng | 2015-03-27
31 | CheckOutException | Other | Tanuj | 2015-03-27
32 | FileIOException | Other | Tanuj | 2015-03-27
33 | System Integrate |  | ALL | 2015-04-04
34 | System Testing |  | ALL | 2015-04-04
35 | CA Report |  | ALL | 2015-04-04
36 | .bat files |  | Xu Minsheng | 2015-04-04
Note on H2: 60 - implement entity & Mgr 70 - implement Dao 85 - finish Unit Test 100 - finish peer review

## CRUD
CRUD : CREATE,READ,UPDATE,DELETE
| Functionality | Category | Product | vendor | transaction | discount | Member | Storekeeper
| System Initiate | R | R | R | R | R | R | R
| System shutdown | C | C | C | C | C | C | C
| login | [6 empty] | R
| checkout |  | RU |  | C | R | RU
| checkInventory |  | R
| generateOrder |  | U | R
| newMember | [5 empty] | C
| newProduct | R | C
| newCategory | CR |  | C
report
| category | R
| product | R | R
| transaction |  | R |  | R |  | R
| member | [5 empty] | R
| Output strategy | Append | Overwrite | Append | Append | - | Overwrite | -

## Assumption
No. | Assumption
1 | Category management should provide vendor management function
2 | Save a snapshot of relevant product's price in [transaction.dat] file
3
4

## coding WBS
No. | Task (class name) | PackageName | Category | undertaker | due date | Specification
1 | Storekeeper |  | domain | Charan |  | Mgr,Dao,TestCase | Mr. Orange
2 | Customer(Abstract) |  | domain | Achyut |  |  | Mr. Blue
3 | Member |  | domain | Achyut |  | Mgr,Dao,TestCase | Mr. Blue
4 | Public |  | domain | Achyut |  |  | Mr. Blue
5 | Transaction |  | domain | Liu Xinzhuo |  | Mgr,Dao,TestCase | Mr. Red
6 | TransactionItem |  | domain | Liu Xinzhuo |  | TestCase | Mr. Red
7 | Product |  | domain | Xie Jiabao |  | Mgr,Dao,TestCase | Mr. Purple
8 | Category |  | domain | Avishek |  | Mgr,Dao,TestCase | Mr. Brown
9 | Vendor |  | domain | Avishek |  | Mgr,Dao,TestCase | Mr. Brown
10 | PurchaseOrder |  | domain(expanded) | Xie Jiabao |  | TestCase | Mr. Purple
11 | Discount(Abstract) |  | domain | Tanuj |  | Mgr,Dao | Mr. Black
12 | MemberDiscount |  | domain | Tanuj |  | TestCase | Mr. Black
13 | OccasionalDiscount |  | domain | Tanuj |  | TestCase | Mr. Black
14 | Store |  | domain | Xu Minsheng |  | TestCase | Mr. White
15 | StoreApplication |  | Controller | Xu Minsheng |  |  | Mr. White
16 | LoginScreen |  | UI | Charan |  |  | Mr. Orange
17 | MainMenu |  | UI | Charan |  |  | Mr. Orange
18 | CheckOutScreen |  | UI | Liu Xinzhuo |  | Check Out process. print receipt. | Mr. Red
19 | CheckInventoryScreen |  | UI | Xie Jiabao |  | generate purchase order and print to console | Mr. Purple
20 | MemberListScreen |  | UI(expanded) | Achyut |  | List all. Provide DELETE function? | Mr. Blue
21 | MemberDialog |  | UI | Achyut |  | Create. Update? | Mr. Blue
22 | ProductListScreen |  | UI(expanded) | Xie Jiabao |  | List all. Provide DELETE function? | Mr. Purple
23 | ProductDialog |  | UI | Xie Jiabao |  | Create. Update? | Mr. Purple
24 | CategoryListScreen |  | UI(expanded) | Avishek |  | List all. Provide DELETE function? | Mr. Brown
25 | CategoryDialog |  | UI | Avishek |  | Create. Update? | Mr. Brown
26 | NewVendorDialog |  | UI | Avishek |  | Create. Update? | Mr. Brown
27 | ReportScreen |  | UI | Charan |  | 4 kinds of report ? Or just for transaction? | Mr. Orange
28 | Placeholder |  | Other | Tanuj |  | barcode reader/printer, receipt printer | Mr. Black
29 | Util |  | Other | Xu Minsheng |  |  | Mr. White
30 | CheckOutException |  | Other | Tanuj |  |  | Mr. Black
31 | FileIOException |  | Other | Tanuj |  |  | Mr. Black

## Overall
Name |  | leave | back |  | Workload
Achyut | On Site |  |  | Mr. Blue | Average
Avishek | Remote | 2015-03-15 | 2015-03-31 | Mr. Brown | High
Charan | Remote | 2015-03-14 | 2015-03-29 | Mr. Orange | Average
Liu Xinzhuo | On Site |  |  | Mr. Red | High
Tanuj | On Site |  |  | Mr. Black | Average
Xie Jiabao | On Site |  |  | Mr. Purple | High
Xu Minsheng | On Site |  |  | Mr. White | Average
Overall schedule
domain |  | 2015-03-16 | 2015-03-20
UI & Other |  | 2015-03-23 | 2015-03-27
Integration & Test |  | 2015-03-30 | 2015-04-04
submit |  | 2015-04-04